## Phishing project tracker
SY Mini Project Tracker Sheet (Phishing)
Project Start Date: 23-08-2021 Project End Date:
Porject Descreption: .
| Name of Team member | Designation
Project Team Members | S. Utkarsh Rao | Team Leader
| Mohammad Musaib Akhter | Team Member
| Manan Kukreja | Team Member
Task1: | Project documentation.
Task2: | Learning HTML5 and CSS3 for designing website.
Task3: | Designing web pages for the project website.
Task4: | Learning python.
Task5: | Implimenting python for coding the software.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Synopsis and project documentation work. | Preparing synopsis for the proposed project. | Complete | [5 empty] | 100%
|  | Preparing copyright document for the proposed project. | Complete | [5 empty] | 100%
|  | Preparing desired system and flowchart for the proposed project. | Complete | [5 empty] | 100% | In Progress | Low
|  | Preparing viability report for the proposed project. | Complete | [5 empty] | 100%
| Learning HTML5 and CSS3 for designing website | Learning to create layout for web pages. | Complete | [5 empty] | 100%
|  | Learning different operations in CSS3 to add effects to the pages. | Complete | [5 empty] | 100%
|  | Learning to link pages to buttons. | Complete | [5 empty] | 100%
| Designing web pages for the project website | Designing 'Home Page' and 'Download Page' of the website. | Complete | [5 empty] | 100%
|  | Designing 'About', 'Contact Us' and 'Footer' for the page. | Complete | [5 empty] | 100% | Complete | High
Sprint 2 | Learning python | Learning syntax and basics of python. | Complete | [5 empty] | 100%
|  | Learning about packages in python. | In Progress | [5 empty] | 80%
| Implimentating python for coding the software | Checking whether the mail is authentic or not. | On Hold | [5 empty] | 60%
|  | Checking whether the URL is authentic or not. | In Progress | [5 empty] | 90%
On Hold
Overdue